## Scope
V23 |  |  | E = Evergreen T = Move to Target Platform (Technical or Dynamic Platform)
Region | Entity | Tier# | GSP | SAAS | IDV | PIB | 2g Stories | eCARE | PWS | PCF Gateways | Mobile | NF Comments | Status
Americas | Mexico | Tier #0 | E | E | N/A | E | E | E | T | E | N/A | Does GSP not require evergreening? What is the plan for Mobile? | active
Americas | USA | Tier #0 | E | E | N/A | N/A | E | E | T | E | N/A | Does GSP not require evergreening? 2g stories would also require evergreening | inactive
Americas | Canada | Tier #1 | E | E | N/A | N/A | E | E | T | E | N/A | Does GSP not require evergreening? No more 2g stories to evergreen? | active
Americas | Argentina | Tier #1 | E | E | N/A | N/A | E | E | T | N/A | N/A | No more 2g stories to evergreen? | active
ASIA | Hong Kong | Tier #0 | Selenium | Selenium | OPTIK | N/A | OPTIK | OPTIK | T | N/A | N/A |  | active
ASIA | Bangladesh | Tier #1 | N/A | N/A | OPTIK | OPTIK | OPTIK | OPTIK | E | N/A | N/A | Evergreen for ID&V? Probably best to show evergreen requirements for both PIB and 2g | active
ASIA | Philippines | Tier #1 | E | E | N/A | N/A | E | E | E | N/A | N/A |  | active
ASIA | China | Tier #1 | E | E | N/A | N/A | E | E | E | E | N/A | Does GSP not require evergreening? | active
ASIA | Sri Lanka | Tier #1 | E | E | N/A | N/A | E | E | E | E | N/A | Does GSP not require evergreening? | active
ASIA | Australia | Tier #1 | E | E | E | E | E | E | T | E | N/A | PIB should not N/A since Australia is already on GSP | inactive
ASIA | Indonesia | Tier #1 | N/A | N/A | E | E | E | E | E | N/A | E | Evergreen for ID&V? | inactive
ASIA | Macau | Tier #1 | N/A | N/A | E | E | E | E | E | N/A | N/A | Evergreen for ID&V? | inactive
ASIA | Mauritius | Tier #1 | N/A | N/A | E | E | E | E | E | N/A | N/A | Evergreen for ID&V? | active
ASIA | New Zealand | Tier #1 | N/A | N/A | E | E | E | E | E | N/A | N/A | Evergreen for ID&V? | active
ASIA | Hang Seng | Tier #0 | N/A | N/A | TBC | E | E | E | T | N/A | E | HSBC scope - infrastructure only Evergreen for ID&V? | active
ASIA | India | Tier #1 | N/A | N/A | T | T | T | E | T | N/A | T | Evergreen for ID&V? | active
ASIA | Malaysia | Tier #1 | N/A | N/A | E | E | E | E | T | N/A | E | Evergreen for ID&V? | active
ASIA | Taiwan | Tier #1 | N/A | N/A | E | E | E | E | T | N/A | E | Evergreen for ID&V? | inactive
ASIA | Vietnam | Tier #1 | N/A | N/A | E | E | E | E | E | N/A | E | Evergreen for ID&V? | inactive
ASIA | Singapore | Tier #1 | N/A | N/A | T | T | T | E | T | N/A | T | Evergreen for ID&V? | inactive
Europe | UK | Tier #0 | E | E | N/A | N/A | T | E | T | N/A | N/A | All customers on Mobile X (TP)? | inactive
Europe | UK (nRFB/CIIOM) | Tier #0 | E | E | N/A | N/A | T | E | N/A | N/A | T | No PWS for CIIOM? Already on AEM when CIIOM went live | inactive
Europe | France | Tier #1 | N/A | N/A | E | N/A | E | E | T | N/A | E | Probably best to show evergreen requirements for both PIB and 2g - France will move PIB to AWS in March therefore not looking to evergreen | inactive
Europe | M&S Bank | Tier #1 | N/A | N/A | E | E | E | E | T | N/A | E |  | inactive
Europe | Armenia | Tier #1 | N/A | N/A | E | E | E | E | T | N/A | E |  | inactive
Europe | Greece | Tier #1 | N/A | N/A | E | E | E | E | T | N/A | E |  | inactive
Europe | Malta | Tier #1 | N/A | N/A | E | E | E | E | T | N/A | E |  | inactive
Europe | Bermuda | Tier #1 | N/A | N/A | E | E | E | E | T | N/A | E |  | inactive
Europe | Expat (Jersey) | Tier #1 | N/A | E | N/A | N/A | T | E | T | E | T | Does GSP not require evergreening? There on PAS so thought it was covered under PCF? PIB should be N/A since Expat already on GSP - agreed 2g stories should show T for plan to migrate to TP - we will move investment buy sell and swith to TP but still not confirmed on pre filled wab forms - meeting with XGTs | inactive
Europe | FD | Tier #0 | N/A | N/A | T | T | T | E | T | TBC?? | T | Can we confirm the evergreen scope for FD? | inactive
Europe | Mortgages | Tier #1 | N/A | N/A | E | N/A | N/A | E | N/A | N/A | N/A |  | inactive
MENA | SABB | Tier #1 | E | E | N/A | N/A | E | E | T | N/A | E |  | inactive
MENA | Egypt | Tier #1 | E | E | N/A | N/A | E | E | T | N/A | E |  | inactive
MENA | Oman | Tier #1 | N/A | E | N/A | E | E | E | T | N/A | E |  | inactive
MENA | Bahrain | Tier #2 | N/A | E | N/A | E | E | E | T | N/A | E |  | inactive
MENA | Qatar | Tier #1 | N/A | E | N/A | E | E | E | T | N/A | E |  | inactive
MENA | Turkey | Tier #1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | If there are no evergreen requirements for Turkey except for OTP, we should show N/A or T for plans to move to target platform | inactive
MENA | UAE | Tier #1 | N/A | E | N/A | E | E | E | T | N/A | E |  | inactive

## Issue
Entity | Issues and Impediments
Mexico | Issue#1
USA | Issue#2
Canada | Impediment1 Impediment2 Impediment3
Argentina | Impediment1 Impediment2
Hong Kong | Impseleniumd imseleniumnt1 Impselenium dimseleniumnt2
Bangladesh | 1. Registration flow is not working, issue reported to Kenny. 2. Not able to download eStatements, issue reported to Kenny, ETA - 03/06.
Philippines | Impedimene1 Impedimene2
China | Impedimene1 Impedimene2
Sri Lanka | Impedimene1 Impedimene2
Australia | Impediment1 Impediment2
Indonesia | Impn/adimn/ane1 Impn/adimn/ane2
Macau | Impn/adimn/ane1 Impn/adimn/ane2
Mauritius | Impn/adimn/ane1 Impn/adimn/ane2
New Zealand | Impn/adimn/ane1 Impn/adimn/ane2
Hang Seng | Impn/adimn/ant1 Impn/adimn/ant2
India | Impn/adimn/ant1 Impn/adimn/ant2
Malaysia | Impn/adimn/ant1 Impn/adimn/ant2
Taiwan | Impn/adimn/ant1 Impn/adimn/ant2
Vietnam | Impn/adimn/ane1 Impn/adimn/ane2
Singapore | Impn/adimn/ant1 Impn/adimn/ant2
UK | Impediment1 Impediment2
UK (nRFB/CIIOM) | Impedimenn/a1 Impedimenn/a2
France | Impn/adimn/ant1 Impn/adimn/ant2
M&S Bank | Impn/adimn/ant1 Impn/adimn/ant2
Armenia | Impn/adimn/ant1 Impn/adimn/ant2
Greece | Impn/adimn/ant1 Impn/adimn/ant2
Malta | Impn/adimn/ant1 Impn/adimn/ant2
Bermuda | Impn/adimn/ant1 Impn/adimn/ant2
Expat (Jersey) | Impn/adimn/ant1 Impn/adimn/ant2
FD | Impn/adimn/ant1 Impn/adimn/ant2
Mortgages | Impn/adimn/ann/a1 Impn/adimn/ann/a2
SABB | Impediment1 Impediment2
Egypt | Impediment1 Impediment2
Oman | Impn/adimn/ant1 Impn/adimn/ant2
Bahrain | Impn/adimn/ant1 Impn/adimn/ant2
Qatar | Impn/adimn/ant1 Impn/adimn/ant2
Turkey | Impn/adimn/ann/a1 Impn/adimn/ann/a2
UAE | Impn/adimn/ant1 Impn/adimn/ant2

## stakeholders
Julie Walker | Progran Test Manager
Julie Walker | Progran Test Manager

## Resources
Resource Name | Entity
Alok Chahande | HK
Amritesh Ranjan | DAK
Parth Rastogi | HK
Krishna Chuka | DAK
Pranita Mane | HK
Khemchand Prasad | DAK
Sayan Banerjee | HK
Seema | BAN
Shwetank Srivastava | Malaysia
Neha Rani | Thailand
Parveen Jalihal | BAN

## pf
Entity | Passed | Failed | Blocked | Not Completed | NA | No Run
Mexico | 10 | 1 | 3 | 1 | 1 | 2
USA | 8 | 2 | 2 | 2 | 2 | 4
Canada | 12 | 3 | 1 | 3 | 1 | 1
Argentina | 14 | 4 | 1 | 1 | 2 | 2
Hong Kong | 15 | 1 | 1 | 2 | 3 | 3
Bangladesh | 10 | 1 | 1 | 3 | 1 | 1
Philippines | 8 | 1 | 1 | 1 | 2 | 2
China | 12 | 1 | 1 | 2 | 3 | 3
Sri Lanka | 14 | 1 | 2 | 3 | 1 | 1
Australia | 15 | 2 | 1 | 1 | 2 | 2
Indonesia | 10 | 1 | 1 | 2 | 3 | 3
Macau | 8 | 1 | 1 | 3 | 1 | 1
Mauritius | 12 | 1 | 1 | 1 | 2 | 2
New Zealand | 14 | 1 | 1 | 2 | 3 | 3
Hang Seng | 15 | 10 | 1 | 3 | 1 | 1
India | 10 | 5 | 1 | 1 | 2 | 2
Malaysia | 8 | 4 | 3 | 2 | 3 | 3
Taiwan | 12 | 3 | 1 | 3 | 1 | 1
Vietnam | 14 | 2 | 1 | 1 | 1 | 2
Singapore | 15 | 1 | 1 | 2 | 2 | 3
UK | 10 | 0 | 1 | 3 | 3 | 1
UK (nRFB/CIIOM) | 8 | 1 | 1 | 1 | 1 | 2
France | 12 | 1 | 1 | 2 | 2 | 3
M&S Bank | 14 | 10 | 1 | 3 | 3 | 1
Armenia | 15 | 5 | 0 | 3 | 1 | 2
Greece | 10 | 4 | 0 | 1 | 2 | 3
Malta | 8 | 3 | 0 | 2 | 3 | 3
Bermuda | 12 | 1 | 0 | 3 | 1 | 1
Expat (Jersey) | 14 | 1 | 0 | 1 | 2 | 2
FD | 15 | 10 | 0 | 2 | 3 | 3
Mortgages | 10 | 5 | 0 | 3 | 1 | 1
SABB | 8 | 4 | 0 | 1 | 2 | 2
Egypt | 12 | 3 | 0 | 2 | 3 | 3
Oman | 14 | 1 | 1 | 3 | 3 | 1
Bahrain | 15 | 1 | 1 | 1 | 1 | 2
Qatar | 10 | 1 | 1 | 2 | 2 | 0
Turkey | 199 | 5 | 1 | 3 | 3 | 1
UAE | 12 | 4 | 1 | 1 | 3 | 2

## pf formulae
Entity | Passed | Failed | Blocked | Not Completed | NA | No Run | Total | Pass pct | Failed And Blocked pct | Total Execution pct
Mexico | 10 | 1 | 3 | 1 | 1 | 2 | 18 | 55.5556 | 22.2222 | 61.1111
USA | 8 | 2 | 2 | 2 | 2 | 4 | 20 | 40 | 20 | 50
Canada | 12 | 3 | 1 | 3 | 1 | 1 | 21 | 57.1429 | 19.0476 | 61.9048
Argentina | 14 | 4 | 1 | 1 | 2 | 2 | 24 | 58.3333 | 20.8333 | 66.6667
Hong Kong | 15 | 1 | 1 | 2 | 3 | 3 | 25 | 60 | 8 | 72
Bangladesh | 10 | 1 | 1 | 3 | 1 | 1 | 17 | 58.8235 | 11.7647 | 64.7059
Philippines | 8 | 1 | 1 | 1 | 2 | 2 | 15 | 53.3333 | 13.3333 | 66.6667
China | 12 | 1 | 1 | 2 | 3 | 3 | 22 | 54.5455 | 9.0909 | 68.1818
Sri Lanka | 14 | 1 | 2 | 3 | 1 | 1 | 22 | 63.6364 | 13.6364 | 68.1818
Australia | 15 | 2 | 1 | 1 | 2 | 2 | 23 | 65.2174 | 13.0435 | 73.913
Indonesia | 10 | 1 | 1 | 2 | 3 | 3 | 20 | 50 | 10 | 65
Macau | 8 | 1 | 1 | 3 | 1 | 1 | 15 | 53.3333 | 13.3333 | 60
Mauritius | 12 | 1 | 1 | 1 | 2 | 2 | 19 | 63.1579 | 10.5263 | 73.6842
New Zealand | 14 | 1 | 1 | 2 | 3 | 3 | 24 | 58.3333 | 8.3333 | 70.8333
Hang Seng | 15 | 10 | 1 | 3 | 1 | 1 | 31 | 48.3871 | 35.4839 | 51.6129
India | 10 | 5 | 1 | 1 | 2 | 2 | 21 | 47.619 | 28.5714 | 57.1429
Malaysia | 8 | 4 | 3 | 2 | 3 | 3 | 23 | 34.7826 | 30.4348 | 47.8261
Taiwan | 12 | 3 | 1 | 3 | 1 | 1 | 21 | 57.1429 | 19.0476 | 61.9048
Vietnam | 14 | 2 | 1 | 1 | 1 | 2 | 21 | 66.6667 | 14.2857 | 71.4286
Singapore | 15 | 1 | 1 | 2 | 2 | 3 | 24 | 62.5 | 8.3333 | 70.8333
UK | 10 | 0 | 1 | 3 | 3 | 1 | 18 | 55.5556 | 5.5556 | 72.2222
UK (nRFB/CIIOM) | 8 | 1 | 1 | 1 | 1 | 2 | 14 | 57.1429 | 14.2857 | 64.2857
France | 12 | 1 | 1 | 2 | 2 | 3 | 21 | 57.1429 | 9.5238 | 66.6667
M&S Bank | 14 | 10 | 1 | 3 | 3 | 1 | 32 | 43.75 | 34.375 | 53.125
Armenia | 15 | 5 | 0 | 3 | 1 | 2 | 26 | 57.6923 | 19.2308 | 61.5385
Greece | 10 | 4 | 0 | 1 | 2 | 3 | 20 | 50 | 20 | 60
Malta | 8 | 3 | 0 | 2 | 3 | 3 | 19 | 42.1053 | 15.7895 | 57.8947
Bermuda | 12 | 1 | 0 | 3 | 1 | 1 | 18 | 66.6667 | 5.5556 | 72.2222
Expat (Jersey) | 14 | 1 | 0 | 1 | 2 | 2 | 20 | 70 | 5 | 80
FD | 15 | 10 | 0 | 2 | 3 | 3 | 33 | 45.4545 | 30.303 | 54.5455
Mortgages | 10 | 5 | 0 | 3 | 1 | 1 | 20 | 50 | 25 | 55
SABB | 8 | 4 | 0 | 1 | 2 | 2 | 17 | 47.0588 | 23.5294 | 58.8235
Egypt | 12 | 3 | 0 | 2 | 3 | 3 | 23 | 52.1739 | 13.0435 | 65.2174
Oman | 14 | 1 | 1 | 3 | 3 | 1 | 23 | 60.8696 | 8.6957 | 73.913
Bahrain | 15 | 1 | 1 | 1 | 1 | 2 | 21 | 71.4286 | 9.5238 | 76.1905
Qatar | 10 | 1 | 1 | 2 | 2 | 0 | 16 | 62.5 | 12.5 | 75
Turkey | 199 | 5 | 1 | 3 | 3 | 1 | 212 | 93.8679 | 2.8302 | 95.283
UAE | 12 | 4 | 1 | 1 | 3 | 2 | 23 | 52.1739 | 21.7391 | 65.2174

## funs
Function | No. of Scenarios | Scripts Recorded # | Scripts Executed #
Pay bills | 61 | 61 | 61
Transfer | 206 | 206 | 206
Rate Enquiry | 8 | 8 | 8
Services | 51 | 51 | 51
View set up Statements advices | 12 | 12 | 12
Alert Services | 2 | 2 | 2
Contact centre | 30 | 30 | 30
Terms and Conditions | 1 | 1 | 1
Account Summary | 11 | 11 | 11
Saas Function | 66 | 66 | 66
Ecare | 31 | 31 | 31
Footer link | 1 | 1 | 1
Header link | 1 | 1 | 1
Fraud feed | to be validated manually
Total | 481 | 481 | 481

## schedule
Entity | Status(scenarios created) | End date
Bangladesh Pass 1 | To be started | 6th March 18
Bangladesh Pass 2 | To be started | 20th March 18

## mindmap schedule
Entity | Status(scenarios created) | Start date
Bangladesh Pass 6 | To be started | 6th March 18
Bangladesh Pass 4 | f | g

## execution
Entity | Passed | Failed | Blocked | No run | Total | Pass% | Failed & Blocked % | Total Execution %
Mexico | 25 | 5 | 2 | 5 | 37 | 67.5676 | 18.9189 | 81.0811
USA | 26 | 6 | 3 | 6 | 41 | 63.4146 | 21.9512 | 78.0488
Canada | 27 | 7 | 4 | 7 | 45 | 60 | 24.4444 | 75.5556
Argentina | 28 | 8 | 5 | 8 | 49 | 57.1429 | 26.5306 | 73.4694
Hong Kong | 29 | 9 | 6 | 9 | 53 | 54.717 | 28.3019 | 71.6981
Bangladesh | 30 | 10 | 7 | 10 | 57 | 52.6316 | 29.8246 | 70.1754
Philippines | 31 | 11 | 8 | 11 | 61 | 50.8197 | 31.1475 | 68.8525
China | 32 | 12 | 9 | 12 | 65 | 49.2308 | 32.3077 | 67.6923
Sri Lanka | 33 | 13 | 10 | 13 | 69 | 47.8261 | 33.3333 | 66.6667
Australia | 34 | 14 | 11 | 14 | 73 | 46.5753 | 34.2466 | 65.7534
Indonesia | 35 | 15 | 12 | 15 | 77 | 45.4545 | 35.0649 | 64.9351
Macau | 36 | 16 | 13 | 16 | 81 | 44.4444 | 35.8025 | 64.1975
Mauritius | 37 | 17 | 14 | 17 | 85 | 43.5294 | 36.4706 | 63.5294
New Zealand | 38 | 18 | 15 | 18 | 89 | 42.6966 | 37.0787 | 62.9213
Hang Seng | 39 | 19 | 16 | 19 | 93 | 41.9355 | 37.6344 | 62.3656
India | 40 | 20 | 17 | 20 | 97 | 41.2371 | 38.1443 | 61.8557
Malaysia | 41 | 21 | 18 | 21 | 101 | 40.5941 | 38.6139 | 61.3861
Taiwan | 42 | 22 | 19 | 22 | 105 | 40 | 39.0476 | 60.9524
Vietnam | 43 | 23 | 20 | 23 | 109 | 39.4495 | 39.4495 | 60.5505
Singapore | 44 | 24 | 21 | 24 | 113 | 38.9381 | 39.823 | 60.177
UK | 45 | 25 | 22 | 25 | 117 | 38.4615 | 40.1709 | 59.8291
UK (nRFB/CIIOM) | 46 | 26 | 23 | 26 | 121 | 38.0165 | 40.4959 | 59.5041
France | 47 | 27 | 24 | 27 | 125 | 37.6 | 40.8 | 59.2
M&S Bank | 48 | 28 | 25 | 28 | 129 | 37.2093 | 41.0853 | 58.9147
Armenia | 49 | 29 | 26 | 29 | 133 | 36.8421 | 41.3534 | 58.6466
Greece | 50 | 30 | 27 | 30 | 137 | 36.4964 | 41.6058 | 58.3942
Malta | 51 | 31 | 28 | 31 | 141 | 36.1702 | 41.844 | 58.156
Bermuda | 52 | 32 | 29 | 32 | 145 | 35.8621 | 42.069 | 57.931
Expat (Jersey) | 53 | 33 | 30 | 33 | 149 | 35.5705 | 42.2819 | 57.7181
FD | 54 | 34 | 31 | 34 | 153 | 35.2941 | 42.4837 | 57.5163
Mortgages | 55 | 35 | 32 | 35 | 157 | 35.0318 | 42.6752 | 57.3248
SABB | 56 | 36 | 33 | 36 | 161 | 34.7826 | 42.8571 | 57.1429
Egypt | 57 | 37 | 34 | 37 | 165 | 34.5455 | 43.0303 | 56.9697
Oman | 58 | 38 | 35 | 38 | 169 | 34.3195 | 43.1953 | 56.8047
Bahrain | 59 | 39 | 36 | 39 | 173 | 34.104 | 43.3526 | 56.6474
Qatar | 60 | 40 | 37 | 40 | 177 | 33.8983 | 43.5028 | 56.4972
Turkey | 61 | 41 | 38 | 41 | 181 | 33.7017 | 43.6464 | 56.3536
UAE | 62 | 42 | 39 | 42 | 185 | 33.5135 | 43.7838 | 56.2162

## excec formulas
Entity | Passed | Failed | Blocked | No run | Total | Pass% | Failed & Blocked % | Total Execution %
Mexico | 25 | 5 | 2 | 5 | 37 | 67.5676 | 18.9189 | 81.0811
USA | 26 | 6 | 3 | 6 | 41 | 63.4146 | 21.9512 | 78.0488
Canada | 27 | 7 | 4 | 7 | 45 | 60 | 24.4444 | 75.5556
Argentina | 28 | 8 | 5 | 8 | 49 | 57.1429 | 26.5306 | 73.4694
Hong Kong | 29 | 9 | 6 | 9 | 53 | 54.717 | 28.3019 | 71.6981
Bangladesh | 30 | 10 | 7 | 10 | 57 | 52.6316 | 29.8246 | 70.1754
Philippines | 31 | 11 | 8 | 11 | 61 | 50.8197 | 31.1475 | 68.8525
China | 32 | 12 | 9 | 12 | 65 | 49.2308 | 32.3077 | 67.6923
Sri Lanka | 33 | 13 | 10 | 13 | 69 | 47.8261 | 33.3333 | 66.6667
Australia | 34 | 14 | 11 | 14 | 73 | 46.5753 | 34.2466 | 65.7534
Indonesia | 35 | 15 | 12 | 15 | 77 | 45.4545 | 35.0649 | 64.9351
Macau | 36 | 16 | 13 | 16 | 81 | 44.4444 | 35.8025 | 64.1975
Mauritius | 37 | 17 | 14 | 17 | 85 | 43.5294 | 36.4706 | 63.5294
New Zealand | 38 | 18 | 15 | 18 | 89 | 42.6966 | 37.0787 | 62.9213
Hang Seng | 39 | 19 | 16 | 19 | 93 | 41.9355 | 37.6344 | 62.3656
India | 40 | 20 | 17 | 20 | 97 | 41.2371 | 38.1443 | 61.8557
Malaysia | 41 | 21 | 18 | 21 | 101 | 40.5941 | 38.6139 | 61.3861
Taiwan | 42 | 22 | 19 | 22 | 105 | 40 | 39.0476 | 60.9524
Vietnam | 43 | 23 | 20 | 23 | 109 | 39.4495 | 39.4495 | 60.5505
Singapore | 44 | 24 | 21 | 24 | 113 | 38.9381 | 39.823 | 60.177
UK | 45 | 25 | 22 | 25 | 117 | 38.4615 | 40.1709 | 59.8291
UK (nRFB/CIIOM) | 46 | 26 | 23 | 26 | 121 | 38.0165 | 40.4959 | 59.5041
France | 47 | 27 | 24 | 27 | 125 | 37.6 | 40.8 | 59.2
M&S Bank | 48 | 28 | 25 | 28 | 129 | 37.2093 | 41.0853 | 58.9147
Armenia | 49 | 29 | 26 | 29 | 133 | 36.8421 | 41.3534 | 58.6466
Greece | 50 | 30 | 27 | 30 | 137 | 36.4964 | 41.6058 | 58.3942
Malta | 51 | 31 | 28 | 31 | 141 | 36.1702 | 41.844 | 58.156
Bermuda | 52 | 32 | 29 | 32 | 145 | 35.8621 | 42.069 | 57.931
Expat (Jersey) | 53 | 33 | 30 | 33 | 149 | 35.5705 | 42.2819 | 57.7181
FD | 54 | 34 | 31 | 34 | 153 | 35.2941 | 42.4837 | 57.5163
Mortgages | 55 | 35 | 32 | 35 | 157 | 35.0318 | 42.6752 | 57.3248
SABB | 56 | 36 | 33 | 36 | 161 | 34.7826 | 42.8571 | 57.1429
Egypt | 57 | 37 | 34 | 37 | 165 | 34.5455 | 43.0303 | 56.9697
Oman | 58 | 38 | 35 | 38 | 169 | 34.3195 | 43.1953 | 56.8047
Bahrain | 59 | 39 | 36 | 39 | 173 | 34.104 | 43.3526 | 56.6474
Qatar | 60 | 40 | 37 | 40 | 177 | 33.8983 | 43.5028 | 56.4972
Turkey | 61 | 41 | 38 | 41 | 181 | 33.7017 | 43.6464 | 56.3536
UAE | 62 | 42 | 39 | 42 | 185 | 33.5135 | 43.7838 | 56.2162

## defects
Entity | High Severity | Medium Severity | Low Severity | Total defects
Mexico | 4 | 7 | 9 | 20
USA | 3 | 8 | 15 | 26
Canada | 2 | 9 | 21 | 32
Argentina | 1 | 10 | 27 | 38
Hong Kong | 0 | 11 | 33 | 44
Bangladesh | 5 | 12 | 39 | 56
Philippines | 9 | 13 | 45 | 67
China | 1 | 14 | 51 | 66
Sri Lanka | 6 | 7 | 9 | 22
Australia | 6 | 7 | 9 | 22
Indonesia | 6 | 7 | 9 | 22
Macau | 6 | 7 | 9 | 22
Mauritius | 6 | 7 | 9 | 22
New Zealand | 6 | 7 | 9 | 22
Hang Seng | 6 | 7 | 9 | 22
India | 6 | 7 | 9 | 22
Malaysia | 6 | 7 | 9 | 22
Taiwan | 6 | 7 | 9 | 22
Vietnam | 6 | 7 | 9 | 22
Singapore | 6 | 7 | 9 | 22
UK | 6 | 7 | 9 | 22
UK (nRFB/CIIOM) | 6 | 7 | 9 | 22
France | 6 | 7 | 9 | 22
M&S Bank | 6 | 7 | 9 | 22
Armenia | 6 | 7 | 9 | 22
Greece | 6 | 7 | 9 | 22
Malta | 6 | 7 | 9 | 22
Bermuda | 6 | 7 | 9 | 22
Expat (Jersey) | 6 | 7 | 9 | 22
FD | 6 | 7 | 9 | 22
Mortgages | 6 | 7 | 9 | 22
SABB | 6 | 7 | 9 | 22
Egypt | 6 | 7 | 9 | 22
Oman | 6 | 7 | 9 | 22
Bahrain | 6 | 7 | 9 | 22
Qatar | 6 | 7 | 9 | 22
Turkey | 6 | 7 | 9 | 22
UAE | 6 | 7 | 9 | 22

## scurve
Project Daily Progress
Estimated # of Scripts |  | 481 |  |  |  | Project Name |  | Evergreen
Actual # of Scripts |  | 481 |  |  |  | Planned Start Date |  | 2018-02-12
# of N/A Scripts |  | 0 |  |  |  | Planned End Date |  | 2018-02-16
# of New Scripts Added |  | 0 |  |  |  | Revised End Date
Todays Date
Project Day | Week Day | Date | Required Pass (Daily) | Daily Pass % Passed (Cumulative) | Number of Scripts | Number of Scripts Marked N/A | Number of Scripts Added | Required Number Script Passed (Cumulative) | Actual # Script Passed (Cumulative) | Actual % Passed (Cumulative) | Actual # of Daily Script Passed | Catch-up daily # of pass scripts required
1 | Mon | 2018-02-12 | 94.4312 | 19.63% | 481 |  |  | 94.4312 | 94 | 19.54% | 94
2 | Tue | 2018-02-13 | 203.1266 | 61.86% | 481 |  |  | 297.5578 | 120 | 24.95% | 26
3 | Wed | 2018-02-14 | 130.4583 | 88.98% | 481 |  |  | 428.0162 | 230 | 47.82% | 110
4 | Thu | 2018-02-15 | 39.8993 | 97.28% | 481 |  |  | 467.9155 | 430 | 89.4% | 200
5 | Fri | 2018-02-16 | 13.0845 | 100% | 481 |  |  | 481 | 481 | 100% | 51

## Defect tracking
Entity | Defect | status | summary | severity | Assigned to | Team Assigned To | ETC
Bangladesh | Defect 1 | Assigned | summary1 | Medium | Tester1 | Team1 | 12
Bangladesh | Defect 2 | Closed | Summary2 | High | Tester2 | Team4 | 24
Bangladesh | Defect 3 | Deferred | summary3 | Low | Tester3 | Team2 | 8
Hong Kong | Defect 8 | Rejected | Summary4 | Medium | Tester4 | Team3 | 5
Hong Kong | Defect 3 | Assigned | summary5 | High | Tester5 | Team1 | 4
Hong Kong | Defect 6 | Closed | summary6 | Low | Tester6 | Team4 | 7
Hong Kong | Defect 10 | Deferred | summary7 | Low | Tester7 | Team2 | 9
Vietnam | Defect 14 | Closed | summary8 | High | Tester8 | Team3 | 1
Vietnam | Defect 22 | Assigned | summary9 | Low | Tester9 | Team1 | 3
Vietnam | Defect 34 | Closed | summary10 | Medium | Tester10 | Team4 | 2
Malaysia | Defect 14 | Closed | summary11 | Medium | Tester11 | Team2 | 3
Malaysia | Defect13 | Assigned | summary4 | High | Tester4 | Team1 | 4
Malaysia | Defect14 | Assigned | summary5 | High | Tester5 | Team2 | 4
China | Defect15 | Assigned | summary6 | Low | Tester6 | Team3 | 4
China | Defect16 | Assigned | summary7 | Low | Tester7 | Team4 | 4
China | Defect17 | Assigned | summary8 | Low | Tester8 | Team5 | 4